## Timeline
Board - Employee management system prototype gantt chart (by weeks)
|  |  | Jun-2021 | [23 empty] | Jul-2021 | [30 empty] | Aug-2021
| Start | End | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
none - Planning |  |  | Jun-2021 7: Planning
Define scope, requirements and approach(Define scope, requirements and approach) | 07-Jun-2021 | 13-Jun-2021 | Jun-2021 7: Define scope, requirements and approach (07-Jun-21 - 13-Jun-21)
Deliverable components( e.g WBS, SWOT analysis)(Deliverable components( e.g WBS, SWOT analysis)) | 07-Jun-2021 | 11-Jun-2021 | Jun-2021 7: Deliverable components( e.g WBS, SWOT analysis) (07-Jun-21 - 11-Jun-21)
Specification UML(Specification UML) | 12-Jun-2021 | 15-Jun-2021 | Jun-2021 12: Specification UML (12-Jun-21 - 15-Jun-21)
Functional specification (Use cases)(Functional specification (Use cases)) | 15-Jun-2021 | 20-Jun-2021 | Jun-2021 15: Functional specification (Use cases) (15-Jun-21 - 20-Jun-21)
Technical specification(Technical specification) | 15-Jun-2021 | 20-Jun-2021 | Jun-2021 15: Technical specification (15-Jun-21 - 20-Jun-21)
none - Research and content |  |  | Jun-2021 7: Research and content
Maket Analysis(Maket Analysis) | 20-Jun-2021 | 22-Jun-2021 | Jun-2021 20: Maket Analysis (20-Jun-21 - 22-Jun-21)
Early prototype (Strength and weakness)(Early prototype (Strength and weakness)) | 20-Jun-2021 | 24-Jun-2021 | Jun-2021 20: Early prototype (Strength and weakness) (20-Jun-21 - 24-Jun-21)
Challenges associated with working domain(Challenges associated with working domain) | 22-Jun-2021 | 24-Jun-2021 | Jun-2021 22: Challenges associated with working domain (22-Jun-21 - 24-Jun-21)
none - Design and Development |  |  | Jun-2021 7: Design and Development
Product wireframes(Product wireframes) | 24-Jun-2021 | 26-Jun-2021 | Jun-2021 24: Product wireframes (24-Jun-21 - 26-Jun-21)
Product prototype design(Product prototype design) | 24-Jun-2021 | 01-Jul-2021 | Jun-2021 24: Product prototype design (24-Jun-21 - 01-Jul-21)
Survey creation(Survey creation) | 29-Jun-2021 | 01-Jul-2021 | Jun-2021 29: Survey creation (29-Jun-21 - 01-Jul-21)
none - Testing and review |  |  | Jun-2021 7: Testing and review
User acceptance testing(User acceptance testing) | 01-Jul-2021 | 03-Jul-2021 | Jul-2021 1: User acceptance testing (01-Jul-21 - 03-Jul-21)
Survey analysis(Survey analysis) | 01-Jul-2021 | 04-Jul-2021 | Jul-2021 1: Survey analysis (01-Jul-21 - 04-Jul-21)
Final evaluation and reflection(Final evaluation and reflection) | 04-Jul-2021 | 05-Jul-2021 | Jul-2021 4: Final evaluation and reflection (04-Jul-21 - 05-Jul-21)